## Project schedule
| Laundry System | [5 empty] | Project start: | [7 empty] | 2025-05-15
[7 empty] | Display week: | [7 empty] | 1
| TASK | ASSIGNED TO | PROGRESS | ACTUAL START | EXPECTED END |  | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Define goals | All Members | 100% | 2025-05-15 | 2025-05-16 | 2
| Project Charter and Architecture | Chetan Sapkal | 100% | 2025-05-16 | 2025-05-17 | 2
Planning and design
| Wireframe Creation | Chetan Talele | 100% | 2025-05-20 | 2025-05-20 | 1
| Payment Gateway Research | Chetan Sapkal & Prathamesh Kapadne | 100% | 2025-05-20 | 2025-05-21 | 2
| ERD Design | Chetan Sapkal & Chetan Talele | 100% | 2025-05-27 | 2025-05-29 | 3
| System Architecture Plan | Yash Borkar | 100% | 2025-05-29 | 2025-05-30 | 2
| RACI Chart Preparation | Chetan Talele | 100% | 2025-05-30 | 2025-05-30
Execution
| Update Frontend Components | Prathamesh Kapadne | 100% | 2025-05-31 | 2025-06-02 | 3
| Backend Prep for Payments | Chetan Talele & Chetan Sapkal | 100% | 2025-06-03 | 2025-06-08 | 6
| Integrate Payment Gateway | Chetan Sapkal | 100% | 2025-06-09 | 2025-06-09 | 1
| Develop User Profile Page UI | Prathamesh Kapadne | 50% | 2025-06-09 | 2025-06-11 | 3
| Backend for User Profiles | Chetan Sapkal | 70% | 2025-06-09 | 2025-06-10 | 2
| Add Payment Gateway Info of Service Providers | Chetan Sapkal & Chetan Talele | 0% | 2025-06-11 | 2025-06-15
| Connect User UI to Backend | Yash Borkar | 100% | 2025-06-11 | 2025-06-11 | 1
Evaluation
| Test Payment Flow | Chetan Talele | 0% | 2025-06-12 | 2025-06-13 | 2
| Final UI Enhancements | Prathamesh Kapadne | 0% | 2025-06-13 | 2025-06-14 | 2
| Full System Testing | Yash Borkar | 0% | 2025-06-15 | 2025-06-17 | 3
| Bug Fixes & Final Adjustments | All Members | 0% | 2025-06-17 | 2025-06-20 | 4
| Deployment | All Members | 0% | 2025-06-19 | 2025-06-21 | 3
Insert new rows ABOVE this one

## Schedule
| Laundry System |  |  |  |  | Project start: | 2025-05-15
[6 empty] | Display week: | 1
| TASK | ASSIGNED TO | START | END
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Define goals | All Members | 2025-05-15 | 2025-05-16 | 2
| Project Charter and Architecture | Chetan Sapkal | 2025-05-16 | 2025-05-17 | 2
Planning and design
| Wireframe Creation | Chetan Talele | 2025-05-20 | 2025-05-20 | 1
| Payment Gateway Research | Chetan Sapkal & Prathamesh Kapadne | 2025-05-20 | 2025-05-21 | 2
| ERD Design | Chetan Sapkal | 2025-05-27 | 2025-05-29 | 3
| System Architecture Plan | Yash Borkar | 2025-05-29 | 2025-05-30 | 2
| RACI Chart Preparation | Chetan Talele | 2025-05-30 | 2025-05-30
Execution
| Update Frontend Components | Prathamesh Kapadne | 2025-05-31 | 2025-06-02 | 3
| Backend Prep for Payments | Chetan Talele & Chetan Sapkal | 2025-06-03 | 2025-06-06 | 4
| Integrate Payment Gateway | Yash Borkar | 2025-06-07 | 2025-06-11 | 5
| Develop User Profile Page UI | Prathamesh Kapadne | 2025-06-12 | 2025-06-13 | 2
| Backend for User Profiles | Chetan Sapkal | 2025-06-07 | 2025-06-08 | 2
| Connect User UI to Backend | Yash Borkar | 2025-06-09 | 2025-06-10
Evaluation
| Test Payment Flow | Chetan Talele | 2025-06-10 | 2025-06-11 | 2
| Final UI Enhancements | Prathamesh Kapadne | 2025-06-11 | 2025-06-12 | 2
| Full System Testing | Yash Borkar | 2025-06-13 | 2025-06-15 | 3
| Bug Fixes & Final Adjustments | All Members | 2025-06-15 | 2025-06-18 | 4
| Deployment | All Members | 2025-06-17 | 2025-06-19 | 3
Insert new rows ABOVE this one
Formulas:
START = [START, row above]+1
START = [START, row above]
END = [START]+1
END = [START]