## Test Cases
Test Case ID | Test Case Description | Preconditions | Test Steps | Expected Result | Actual Result | Status | Priority | Comments
TC-001 | User Login Flow | User account exists | 1. Navigate to login page | User is redirected to dashboard with welcome message | User successfully logged in and redirected to dashboard, welcome message displayed correctly | PASS | High | Works smoothly
2. Enter valid credentials
3. Click Login
TC-002 | Login with Invalid Credentials | None | 1. Navigate to login page | Error: "Invalid credentials" | Error message displayed below password field, login prevented | PASS | High | Validation working
2. Enter invalid password
3. Click Login
TC-003 | New User Registration | None | 1. Go to signup page | Account created & redirected to login | User account created successfully, redirected to login page | PASS | High | Email verification not implemented
2. Fill all fields
3. Click Register
TC-004 | Service Browsing | User logged in | 1. Navigate to Services page | All services load with correct names & prices | Service list loaded, images displayed, prices accurate | PASS | High | Images optimized
2. Scroll list
TC-005 | Add Service to Cart | User logged in | 1. Select "Wash & Iron" | Item appears in cart with correct price | Cart updated instantly with "Wash & Iron" and price ₹120 | PASS | High | Works fine
2. Click Add to Cart
TC-006 | Remove Service from Cart | Cart has items | 1. Click "Remove" on service | Item removed & total updated | Item removed, cart total recalculated correctly | PASS | Medium | Smooth update
TC-007 | Proceed to Checkout | Cart has items | 1. Click Checkout | Checkout page displays all items | Checkout page loaded showing 2 items, correct subtotal and total | PASS | High | Accurate calculation
TC-008 | UPI Payment Success | Cart has items, UPI enabled | 1. Select UPI | Payment processed, order marked Paid | UPI payment completed successfully, order status updated to "Paid" | PASS | High | Works as expected
2. Enter test@upi
3. Pay
TC-009 | UPI Payment Failure | Cart has items | 1. Select UPI | Error: "Invalid UPI ID" | Error toast displayed, no transaction initiated | PASS | High | Validation works
2. Enter abc123
3. Pay
TC-010 | Card Payment | Cart has items | 1. Select Card | Payment processed successfully | Payment completed, order status updated | PASS | Medium | Works fine
2. Enter valid details
3. Pay
TC-011 | Order Tracking | User has orders | 1. Go to My Orders | Status and details shown | Order page loaded showing status: "In Progress" and delivery date | PASS | Medium | Accurate info
2. Click recent order
TC-012 | Order Cancellation | Order not started | 1. Go to My Orders | Order marked "Cancelled" | Order updated to "Cancelled" | PASS | Medium | status displayed
2. Click Cancel
TC-013 | Admin – View All Orders | Admin logged in | 1. Go to Dashboard | Orders list with statuses | Orders table loaded with 50 entries, correct filters applied | PASS | High | Works well
2. Click Orders
TC-014 | Admin – Update Order Status | Admin logged in | 1. Change order status | Status updated for user | Status changed to "Delivered" and reflected in user panel | PASS | High | Instant sync
2. Save
TC-015 | API – Get Services | Backend running | 1. GET /services | Returns JSON list | API responded in 120ms with correct JSON list of 10 services | PASS | High | API stable
TC-016 | API – Create Order | Backend running | 1. POST /orders | Order created | API returned 201 Created with order ID #452 | PASS | High | Works fine
TC-017 | API – Payment Webhook | Backend running | 1. Send webhook payload | Order updated | Order #452 updated to "Paid" | PASS | High | Verified via DB
TC-018 | Security – SQL Injection | Backend running | 1. Try ' OR 1=1-- in login | Request blocked | Error returned, no DB crash | PASS | Critical | Protection works
TC-019 | Security – XSS | Backend running | 1. Submit <script>alert(1)</script> | Script blocked | Input sanitized, no alert triggered | PASS | Critical | Safe
TC-020 | Logout Functionality | User logged in | 1. Click Logout | Redirect to login | Redirected to login, session cookie cleared | PASS | Medium | Smooth transition
TC-021 | Performance – Home Load | App live | 1. Load home | Loads <3s | Page loaded in 2.1s | PASS | Low | Good
TC-022 | Mobile Responsiveness | App live | 1. Open on mobile | Layout adjusts | Responsive layout with readable fonts | PASS | Medium | -
TC-023 | Offline Handling | PWA enabled | 1. Disconnect internet | Cached content loads | Cached homepage loaded successfully | PASS | Medium | Works
2. Open cached page